## Product Backlog
ID | Sprint | Main Task | Task Description | Type | Priority | Release | Developer | Hours Estimation | Real Efforts | Status | Created Day | Last Update | Created By
BOOK 6 | Sprint 2 | Database conceptual design: Entity Relationship Diagram. | Design and document the Entity Relationship Diagram to establish the database structure and relationships among entities. | Documents/Report | High | Release | ddhai22@clc.fitus.edu.vn | 4 | 5 | DONE | 2024-10-29 | 2024-11-10 | ptyquyen22@clc.fitus.edu.vn
BOOK 8 | Sprint 2 | UI design: Color palette, main page. | Design the primary color palette and layout for the main page of the application, ensuring alignment with brand style and usability. | Frontend | Medium | V1 | ptyquyen22@clc.fitus.edu.vn | 8 |  | IN PROGRESS (TECHNICAL) | 2024-10-29 | 2024-11-10 | ptyquyen22@clc.fitus.edu.vn
BOOK 9' | Sprint 2 | Weekly reports 1 | Prepare and submit the first weekly report, summarizing progress, challenges, and upcoming goals for the week. | Documents/Report | Medium | Release | tttoan22@clc.fitus.edu.vn | 2 | 1 | DONE | 2024-10-29 | 2024-11-10 | ptyquyen22@clc.fitus.edu.vn
BOOK 9'' | Sprint 2 | Weekly reports 2 | Prepare and submit the second weekly report, detailing weekly achievements, roadblocks, and team updates. | Documents/Report | Medium | Release | tttoan22@clc.fitus.edu.vn | 2 | 1 | DONE | 2024-10-29 | 2024-11-10 | ptyquyen22@clc.fitus.edu.vn
BOOK 44 | Sprint 2 | Plan for Sprint 3. | Create a detailed plan for Sprint 3, including goals, tasks, and a timeline aligned with the project roadmap. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 |  | TO DO | 2024-10-29 | 2024-10-31 | ptyquyen22@clc.fitus.edu.vn
BOOK 45 | Sprint 2 | Sprint 2 Revision. | Review the tasks and outcomes of Sprint 2 to assess completion, identify lessons, and plan carry-over tasks. | Documents/Report | Medium | Release | All members | 2 |  | TO DO | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 54 | Sprint 2 | Write the release plan | Develop a comprehensive release plan that outlines the version rollout, target audience, and key milestones. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-10-29 | 2024-10-31 | ptvinh22@clc.fitus.edu.vn
BOOK 56 | Sprint 2 | Schedule Sprint 2's backlog | Organize and prioritize the backlog items for Sprint 2, allocating resources and setting deadlines for tasks. | Documents/Report | High | Release | ptyquyen22@clc.fitus.edu.vn | 2 | 2 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 57 | Sprint 2 | Draw use-case models | Create visual use-case models that illustrate user interactions and system functionalities for key application features. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 | 6 | DONE | 2024-10-29 | 2024-11-09 | tttoan22@clc.fitus.edu.vn
BOOK 58 | Sprint 2 | Write Use-case specification | Write detailed use-case specifications for project features, including actors, flows, and pre- and post-conditions. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 16 | 14 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 59 | Sprint 2 | Prepare a report detailing the setup of development tools | Document and report on the configuration and setup of development tools, covering IDEs, repositories, and dependencies. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 60 | Sprint 2 | Move all documentations to Confluence. | Transfer all project-related documentation to Confluence, organizing files for easy access and version control. | Documents/Report | Low | Release | ptvinh22@clc.fitus.edu.vn | 2 |  | TO DO | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 61 | Sprint 2 | Project infrastructure setup | Set up the infrastructure needed for the project, including servers, database connections, and repository access. | Backend | High | Release | ddhai22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 62 | Sprint 2 | UI design: log in, sign up | Design the user interface for login and signup screens, focusing on user experience, branding, and security considerations. | Frontend | Medium | V1 | ddhai22@clc.fitus.edu.vn | 8 |  | IN PROGRESS (TECHNICAL) | 2024-10-29 | 2024-11-10 | tttoan22@clc.fitus.edu.vn
BOOK 66 | Sprint 2 | Revised project plan and vision document | Update the project plan and vision document to reflect recent adjustments in scope, timeline, or objectives. | Documents/Report | High | Release | All members | 2 | 1 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 67 | Sprint 2 | Review use-case specification document | Carefully review the use-case specification document to ensure it accurately captures functional requirements, aligns with the project vision, and clearly defines expected user interactions. Provide feedback on areas needing clarification or refinement. | Documents/Report | Medium | Release | ddhai22@clc.fitus.edu.vn | 2 | 1 | DONE | 2024-11-09 | 2024-11-10 | tttoan22@clc.fitus.edu.vn
BOOK 68 | Sprint 2 | Fix use-case specification document | Revise and update the use-case specification document based on feedback and any new project requirements. Ensure that all functional requirements are clearly defined, align with the overall project vision, and provide detailed descriptions of user interactions and system responses. Verify that each use case is complete, accurate, and free of ambiguities. | Documents/Report | High | Release | ptyquyen22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-11-07 | 2024-11-10 | tttoan22@clc.fitus.edu.vn