## Product Backlog
ID | Sprint | Main Task | Task Description | Type | Priority | Release | Developer | Hours Estimation | Real Efforts | Status | Created Day | Last Update | Created By
BOOK 6 | Sprint 2 | Database conceptual design: Entity Relationship Diagram. | Design and document the Entity Relationship Diagram to establish the database structure and relationships among entities. | Documents/Report | High | Release | ddhai22@clc.fitus.edu.vn | 4 | 4 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 8 | Sprint 2 | UI design: Color palette, main page. | Design the primary color palette and layout for the main page of the application, ensuring alignment with brand style and usability. | UI | Medium | Release | ptyquyen22@clc.fitus.edu.vn | 4 | 3 | REVIEW | 2024-10-29 | 2024-11-04 | ptyquyen22@clc.fitus.edu.vn
BOOK 9.1 | Sprint 2 | Weekly reports 1 | Prepare and submit the first weekly report, summarizing progress, challenges, and upcoming goals for the week. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 4 | 4 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 9.2 | Sprint 2 | Weekly reports 2 | Prepare and submit the second weekly report, detailing weekly achievements, roadblocks, and team updates. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 4 | 8 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 44 | Sprint 2 | Plan for Sprint 3. | Create a detailed plan for Sprint 3, including goals, tasks, and a timeline aligned with the project roadmap. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 |  | TO DO | 2024-10-29 | 2024-10-31 | ptyquyen22@clc.fitus.edu.vn
BOOK 45 | Sprint 2 | Sprint 2 Revision. | Review the tasks and outcomes of Sprint 2 to assess completion, identify lessons, and plan carry-over tasks. | Documents/Report | High | Release | All members | 2 |  | TO DO | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 54 | Sprint 2 | Write the release plan | Develop a comprehensive release plan that outlines the version rollout, target audience, and key milestones. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-10-29 | 2024-10-31 | ptvinh22@clc.fitus.edu.vn
BOOK 56 | Sprint 2 | Schedule Sprint 2's backlog | Organize and prioritize the backlog items for Sprint 2, allocating resources and setting deadlines for tasks. | Documents/Report | Medium | Release | ptyquyen22@clc.fitus.edu.vn | 2 | 2 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 57 | Sprint 2 | Draw use-case models | Create visual use-case models that illustrate user interactions and system functionalities for key application features. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 | 6 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | tttoan22@clc.fitus.edu.vn
BOOK 58 | Sprint 2 | Write Use-case specification | Write detailed use-case specifications for project features, including actors, flows, and pre- and post-conditions. | Documents/Report | High | Release | tttoan22@clc.fitus.edu.vn | 16 | 14 | REVIEW | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 59 | Sprint 2 | Prepare a report detailing the setup of development tools | Document and report on the configuration and setup of development tools, covering IDEs, repositories, and dependencies. | Documents/Report | High | Release | ptvinh22@clc.fitus.edu.vn | 4 | 4 | IN PROGRESS (DOCUMENT) | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 60 | Sprint 2 | Move all documentations to Confluence. | Transfer all project-related documentation to Confluence, organizing files for easy access and version control. | Documents/Report | Medium | Release | ptvinh22@clc.fitus.edu.vn | 2 |  | TO DO | 2024-10-29 | 2024-11-09 | ptyquyen22@clc.fitus.edu.vn
BOOK 61 | Sprint 2 | Project infrastructure setup | Set up the infrastructure needed for the project, including servers, database connections, and repository access. | Backend | High | Release | ddhai22@clc.fitus.edu.vn | 4 | 4 | DONE | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 62 | Sprint 2 | UI design: log in, sign up | Design the user interface for login and signup screens, focusing on user experience, branding, and security considerations. | UI | Medium | Release | ddhai22@clc.fitus.edu.vn | 2 | 2 | REVIEW | 2024-10-29 | 2024-11-09 | tttoan22@clc.fitus.edu.vn
BOOK 66 | Sprint 2 | Revised project plan and vision document | Update the project plan and vision document to reflect recent adjustments in scope, timeline, or objectives. | Documents/Report | High | Release | All members | 4 |  | REVIEW | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
BOOK 67 | Sprint 2 | Review use-case specification document | Review the use-case specification document and use-case model about content and format. | Documents/Report | High | Release | ddhai22@clc.fitus.edu.vn | 4 |  |  | 2024-10-29 | 2024-11-09 | ptvinh22@clc.fitus.edu.vn
Note on K2: 1 Pending
Note on K3: 1 Pending
Note on K4: 1 Pending
Note on K5: 1 Pending
Note on K6: 1 Pending
Note on K7: 1 Pending
Note on K8: 1 Pending
Note on K9: 1 Pending
Note on K10: 1 Pending
Note on K11: 1 Pending
Note on K12: 1 Pending
Note on K13: 1 Pending
Note on K14: 1 Pending
Note on K15: 1 Pending
Note on K16: 1 Pending